## Sheet1
S/N | Type | Deliverable | TO DO | Stakeholder | COMPLETED? | ISSUE FACED
1 | Documentation | Class Diagram | Update Methods, Add Boundary and Control Classes
2 | Documentation | Sequence Diagram
3 | Documentation | UCS
4 | Documentation | SRS | Complete SRS
5 | Documentation | Sequence Diagram
6 | Documentation | Design Model
7 | Code | School/Uni/poly Uis | Button Layout | Zixing | COMPLETED
8 | Code | Filter Search for UNI | Filter Search backend | Fab | COMPLETED
9 | Code | Filter Search for UNI | Filter Search frontend | Zixing/Terrence | COMPLETED
10 | Code | Search | Search Backend | Fab | COMPLETED
11 | Code | Search | Search Frontend | Zixing/Terrence | COMPLETED
12 | Dataset | Uni GPA | Clean and add GPA column | Terrence | COMPLETED | unable to get some data but in general those with data are working
13 | Dataset | Course Descriptions | Course description for Uni, ITE, Poly | Zixing
14 | Dataset | ITE | Add which institute | Zixing
15 | Code | CCA and Intake Requirement |  | Terrence | COMPLETED | unable to get some data but in general those with data are working
16 | Code | Standardize UI design |  | All
17 | Code | Format Course Info Desc |  | Zixing | COMPLETED
18 | Code | Icon for each institute | InstitutePage picture display | Zixing | COMPLETED
19 | Documentation | Class Diagram | Add multiplicity
20 | Documentation | Test Case (Manual Testing)
21 | Presentation | Video Walkthrough (5-7 min)
22 | Presentation | Design Process Powerpoint